## Functional
|  | Maconomy Support Team (Near Shore) | [5 empty] | Open -> On going -> Blocked -> Done
Transition Plan checklist
Item ID | num | Maconomy Module, Functionality, Processes | Scope | Solution | Documentation | Doc ID | Implemented? | Self-Study / Test | Self-Study / Test | Training | Open Issues | Status | Last update | Comments | My notes
. |  | . | . | . | . | . | . | Luis Batista | Tiago Delgado | . | . | . |  | .
FUN-001 |  | Maconomy System (Installation and Navigation) | Core | Standard | User Guide | ? | --- | On going | On going | ? | No | On going | 2014-03-27
FUN-002 | 1.3 | Acesses - Users, User Types and accesses levels (change user type, change specif user) | Core | Standard | Solution Description (core model) | 2.5 | --- | Done | On going | 2014-03-24 | Yes | On going | 2014-03-27 | Major Issue (fraud risk for internal control). To change a user imported from EAD, the application forces the user to be deleted and newly created.
FUN-003 | 1 | Business and Financial Model | Core | Standard | Solution Description (core model) | 2.1 | --- | Open | Open | 2014-03-24 |  | On going | 2014-03-27
FUN-004 | 1.7 | Dimensions | Core | Standard | Solution Description (core model) | 2.2 | --- | Done | On going | ? | No | On going | 2014-03-27 | OK
FUN-005 | 1.5 e 1.6 | CoA (Global and Local), subledgers and registration codes | Core | Standard | Solution Description (core model) | 2.2 | --- | Done | On going | 2014-03-24 | No | On going | 2014-03-27 | Block is OK / Delete Global Account NOK
FUN-006 |  | MPD - Registration code per company | Core | Enhancement | Requirements Specification |  | ? | Open | Open | 2014-03-24 |  | On going | 2014-03-27
FUN-007 | 1.4 | OBS/Departments | Core | Standard | Solution Description (core model) | 2.2 | --- | Blocked | On going | 2014-03-24 | Yes | Blocked | 2014-03-27 | Not enough info/doc. Only information views were explored. Blocking a department - Not possible to use.
FUN-008 |  | Companies | Core | Standard | Solution Description (core model) | 2.3 | --- | Open | On going | 2014-03-24 |  | On going | 2014-03-27
FUN-009 |  | Setup - Transaction Types / Groups / Numbers / Posting Periods / Years | Core | Standard | Solution Description (core model) | 2.3 | --- | Open | On going | 2014-03-24 |  | On going | 2014-03-27 | The goal was achieved, but without documentation
FUN-010 | 1.1 e 1.2 | Employees (creation and maintenance) | Core | Standard | Solution Description (core model) e User Guide | 2.4 | --- | Blocked | Blocked | 2014-03-24 | Yes | Blocked | 2014-03-27 | Several issues - no interface testing yet, no full view of information (tables specs are not populated). Not possible to insert any value in vendor no. Not enough info on fields, data and impact of changes. Dependencies. | ?
FUN-011 |  | Activities | Core | Standard | Solution Description (core model) | 2.5 | --- | Open | Open | 2014-03-24 |  | On going | 2014-03-27
FUN-012 | 4 | Business Process O2C | Core | Standard | Solution Description (core model) | 3.1 | --- | Open | On going | 2014-03-25 |  | On going | 2014-03-27 |  | L.Baptista (no comments)
FUN-013 | 4.1 | Customers | Core | Standard | Solution Description (core model) | 3.1 | --- | Open | On going | 2014-03-25 |  | On going | 2014-03-27
FUN-014 | 4.2 | YellowPagiz validation | Core | Standard | Solution Description (core model) and core script tests |  | --- | Open | Blocked |  |  | Blocked | 2014-03-27 | Not possible to test
FUN-015 | 4.3 | Projects (Jobs) | Core | Standard | Solution Description (core model) e User Guide | 3.2 | --- | Open | On going | 2014-03-25 |  | On going | 2014-03-27
FUN-016 | 4.9 | Jobs Employees | Core | Standard | Solution Description (core model) e User Guide | 3.2 | --- | Open | On going | 2014-03-25 |  | On going | 2014-03-27
FUN-017 |  | O2C - Convert to Contracted | Core | Extension | Extension List |  | ? | Open | Open | 2014-03-25 |  | On going | 2014-03-27
FUN-018 |  | O2C - Project Creation | Core | Extension | Extension List |  | ? | Open | Open | 2014-03-25 |  | On going | 2014-03-27
FUN-019 |  | O2C - Customer Creation | Core | Extension | Extension List |  | ? | Open | Open | 2014-03-25 |  | On going | 2014-03-27
FUN-020 |  | Project "Net Job Balance to Accruals or Deferrals" | Core | Enhancement | Requirements Specification; Design |  | ? | Open | Open | 2014-03-25 |  | On going | 2014-03-27
FUN-021 |  | Project "Pricing in Days" | Core | Enhancement | Requirements Specification |  | ? | Open | Open | 2014-03-25 |  | On going | 2014-03-27
FUN-022 | 4.6 | Project Pricing | Core | Standard | Solution Description (core model) and core script tests |  | --- | Open | On going | 2014-03-25 |  | On going | 2014-03-27
FUN-023 |  | Project "Registration in Hours with Rounding to Half and Whole Days for Revenue and Invoicing" | Core | Enhancement | Requirements Specification |  | ? | Open | Open | 2014-03-25 |  | On going | 2014-03-27
FUN-024 |  | Intercompany, Casquette, Transnational, Boost | Core | Standard | Solution Description (core model) | 3.3 | --- | Open | On going | 2014-03-25 |  | On going | 2014-03-27
FUN-025 |  | O2C - Fixed Price Intercompany Jobs | Core | Enhancement | Requirements Specification |  | ? | Open | Open | 2014-03-25 |  | On going | 2014-03-27
FUN-026 |  | Employee allocations | Core | Standard | Solution Description (core model) | 3.4 | --- | Open | On going | 2014-03-25 |  | On going | 2014-03-27
FUN-027 | 4.7 | Project budgets | Core | Standard | Solution Description (core model) e User Guide | 3.5 | --- | Open | On going | 2014-03-25 |  | On going | 2014-03-27
FUN-028 | 4.10, 4.11 e 4.12 | Timesheets and Approvals | Core | Standard | Solution Description (core model) | 3.6 | --- | Open | On going | 2014-03-25 |  | On going | 2014-03-27
FUN-029 |  | O2C - Absence Management | Core | Extension | Extension List |  | ? | Open | Open | 2014-03-25 |  | On going | 2014-03-27
FUN-030 | 4.14 | Project invoicing - T&M | Core | Standard | Solution Description (core model); solution description (detail); User Guide | 3.7 | --- | Open | On going | 2014-03-25 | Yes | On going | 2014-03-27 | The menu is not according to script test. Not clear how to finish the invoice process (only until the draft invoice generation). Error transfering invoice plan to invoice.
FUN-031 | 4.15 | Project invoicing on account | Core | Standard | Solution Description (core model); solution description (detail); User Guide | 3.7 | --- | Open | On going | 2014-03-25 | Yes | On going | 2014-03-27 | The menu is not according to script test. Not clear how to finish the invoice process (only until the draft invoice generation). Error transfering invoice plan to invoice.
FUN-032 | 4.18 | Project invoicing - blanket | Core | Standard | Solution Description (core model); solution description (detail); User Guide | 3.7 | --- | Open | On going | 2014-03-25 | Yes | On going | 2014-03-27 | The menu is not according to script test. Not clear how to finish the invoice process (only until the draft invoice generation). Error transfering invoice plan to invoice.
FUN-033 | 4.17 | Project crediting | Core | Standard | Solution Description (core model); solution description (detail); User Guide | 3.7 | --- | Open | On going | 2014-03-25 | Yes | On going | 2014-03-27
FUN-034 | 4.19 | Customer payment | Core | Standard | Solution Description (core model); solution description (detail); User Guide | 3.7 | --- | Open | On going | 2014-03-25 | No | On going | 2014-03-27
FUN-035 | 4.20 e 4.21 | Customer bad debits (provisions and write-off) | Core | Standard | Solution Description (core model); solution description (detail); User Guide | 3.7 | --- | Open | On going | 2014-03-25 | No | On going | 2014-03-27
FUN-036 | 4.4 e 4.13 | Customer PO | Core | Standard | Solution Description (core model) and core script tests |  | --- | Open | On going | 2014-03-25 |  | On going | 2014-03-27
FUN-037 | 4.5 | Task lists | Core | Standard | Solution Description (core model) and core script tests |  | --- | Open | On going | 2014-03-25 |  | On going | 2014-03-27
FUN-038 | 4.8 e 4.16 | Subscription Order and Invoices | Core | Standard | Solution Description (core model) and core script tests |  | --- | Open | Open | 2014-03-25 | Yes | On going | 2014-03-27 | NOT CLEAR
FUN-039 |  | O2C - Extended Customer PO Handling | Core | Extension | Extension List |  | ? | Open | Open | 2014-03-25 |  | On going | 2014-03-27
FUN-040 |  | O2C - Project with Fixed Monthly Fee "Revenue Plan" | Core | Enhancement | Requirements Specification |  | ? | Open | Open | 2014-03-25 |  | On going | 2014-03-27
FUN-041 | 4.22 e 4.23 | AR Lookups, Reports and balance list | Core | Standard | Solution Description (core model) | 3.8 | --- | Open | Open | 2014-03-25 |  | On going | 2014-03-27
FUN-042 |  | Cash collection, factoring, credit control, reminders, customer payments | Core | Standard | Solution Description (core model) | 3.8 | --- | Open | Open | 2014-03-25 |  | On going | 2014-03-27
FUN-043 |  | O2C - Credit control | Core | Extension | Extension List |  | ? | Open | Open | 2014-03-25 |  | On going | 2014-03-27
FUN-044 | 3.1 | Expenses Sheets | Core | Standard | Solution Description (core model) e User Guide | 4.1 | --- | Done | Done | ? | Yes | On going | 2014-03-27 | When printing all expenses posted to the project are showed and not only the expense created.
FUN-045 |  | P2P - Travel Request Handling | Core | Extension | Extension List |  | ? | Open | Open | 2014-03-26 |  | On going | 2014-03-27
FUN-046 |  | Business Process P2P - Mission Letters | FR, IT | Extension | Extension List; Solution Description (core model) | 4.1 | ? | Open | Open | 2014-03-26 |  | On going | 2014-03-27
FUN-047 | 3 | Business Process P2P | Core | Standard | Solution Description (core model) | 4.2 | --- | On going | On going | 2014-03-26 | No | On going | 2014-03-27
FUN-048 | 3.2 | Vendors | Core | Standard | Solution Description (core model) | 4.2 | --- | On going | On going | 2014-03-26 | Yes | On going | 2014-03-27 | Vendor can be created with blank VAT number
FUN-049 | 3.3 | Requisitions | Core | Standard | Solution Description (core model) e User Guide | 4.3; 4.4 | --- | On going | On going | 2014-03-26 | Yes | On going | 2014-03-27
FUN-050 | 3.3 | Purchase Orders | Core | Standard | Solution Description (core model) e User Guide | 4.3; 4.4 | --- | On going | On going | 2014-03-26 | Yes | On going | 2014-03-27
FUN-051 | 3.4 e 3.5 | Vendors Invoices and Invoices Allocation | Core | Standard | Solution Description (core model) e User Guide | 4.3; 4.4 | --- | On going | On going | 2014-03-26 | Yes | On going | 2014-03-27 | Several issues, error messages and documentation not clear
FUN-052 | 3.6 e 3.8 | Vendors reconciliation and reports | Core | Standard | ? | ? | --- | On going | On going | ? |  | On going | 2014-03-27 | Incorrect documentation, Test option not present in UAT 1
FUN-053 | 3.10 | Vendors lookups and reports | Core | Standard | ? | ? | --- | On going | On going | ? |  | On going | 2014-03-27
FUN-054 | 3.9 | Vendors Payments | Core | Standard | Solution Description (core model) | 4.5 | --- | Open | Blocked | 2014-03-26 | Yes | Blocked | 2014-03-27 | Test option not present in UAT1. Once the creation was not done, it is not possible to do the reconciliation. Not possible to finish. Just proposal creation was done.
FUN-055 |  | Employees Cost Rates, Billable and non-Billable Projects, Direct Margin | Core | Standard | Solution Description (core model) | 5.1; 5.2 | --- | Open | On going | 2014-03-27 |  | On going | 2014-03-27
FUN-056 |  | Progress Evaluation / Revenue Recognition | Core | Standard | Solution Description (core model) | 5.3, 5.4 | --- | Open | On going | 2014-03-27 |  | On going | 2014-03-27 | For "Revenue recognition calculation" - No project that can be used and the invoices to fixed price project could not be done
FUN-057 |  | Taxes - VAT | Core | Standard | Solution Description (core model) | 6.1 | --- | Open | Open | 2014-03-27 |  | On going | 2014-03-27
FUN-058 |  | Taxes - Withholding Tax | Core | Standard | Solution Description (core model) | 6.1 | --- | Open | Open | 2014-03-27 |  | On going | 2014-03-27
FUN-059 |  | Taxes - VAT | Local | ? | ? | ? | --- | Open | Open | 2014-03-27 |  | On going | 2014-03-27
FUN-060 |  | Taxes - Withholding Tax | Local | ? | ? | ? | --- | Open | Open | 2014-03-27 |  | On going | 2014-03-27
FUN-061 |  | VAT on Open Sales | Local | ? | Solution Description (core model) | 6.1 | ? | Open | Open | 2014-03-27 |  | On going | 2014-03-27
FUN-062 |  | VAT Cash Accounting | Core | Extension | Extension List | ? | ? | Open | Open |  |  | On going | 2014-03-27
FUN-063 |  | O2C - VAT on Accrued Cost and Sales | Core | Enhancement | Requirements Specification | ? | ? | Open | Open |  |  | On going | 2014-03-27
FUN-064 |  | Exchange Rates, Importing | Core | Standard | Solution Description (core model) | 6.2 | --- | Open | Open | 2014-03-27 |  | On going | 2014-03-27
FUN-065 |  | Automatic Intercompany Invoicing, Standard Analyzer | Core | Standard | Solution Description (core model) | 6.3 | --- | Open | Open | 2014-03-27 |  | On going | 2014-03-27
FUN-066 |  | O2C - Intercompany Job Cost entries as Open Cost and Open Sales until Invoiced | Core | Enhancement | Requirements Specification |  | ? | Open | Open | 2014-03-27 |  | On going | 2014-03-27
FUN-067 |  | Month End, Reavaluation, Provision, Ageing (WIP) Reporting. Overhhead Allocation, Closing, Year End | Core | Standard | Solution Description (core model) | 6.4 | --- | Open | Open | 2014-03-27 |  | On going | 2014-03-27
FUN-068 | 2.7 | Fixed Assets | Core | Standard | Solution Description (core model), solution description (detail) | 6.5 | --- | Done | Done | 2014-03-27 | Yes | On going | 2014-03-27 | Asset depreciated and verified posting in General Ledger . The list of jounals does not filter correctly the postings
FUN-069 |  | Fixed Assets as Reference | Core | Enhancement | Requirements Specification |  | ? | Open | Open | 2014-03-27 |  | On going | 2014-03-27
FUN-070 |  | Fixed Assets linked to Jobs | Core | Enhancement | Extension List, Requirements Spec, Design Doc |  | ? | Open | Open | 2014-03-27 |  | On going | 2014-03-27
FUN-071 |  | Fixed Assets assigned to Projects (incl. Additional Posting Scripting) | Core | Extension | ? |  | ? | Open | Open | 2014-03-27 |  | On going | 2014-03-27 |  | rever
FUN-072 |  | Banking | Local | ? | Solution Description (core model) | 6.6 | ? | Open | Open | 2014-03-27 |  | On going | 2014-03-27
FUN-073 | 2 | Business Process Accounting | Core | Standard | Solution Description (core model) | 5.1; 5.2 | --- | Open | On going | 2014-03-27 |  | On going | 2014-03-27
FUN-074 |  | Financial Budgets | Core | Standard | Solution Description (core model) | 6.7 | --- | Open | Open | 2014-03-27 |  | On going | 2014-03-27
FUN-075 |  | Financial Budgets - populate new template from old template and actuals | Core | Extension | ? |  | ? | On going | Open | ? | No | On going | 2014-03-27
FUN-076 | 2.1 | General Journals | Core | Standard | None | --- | --- | Blocked | Blocked | ? | Yes | Blocked | 2014-03-27 | Several issues - error with tests (scripts), additional info needed. Missing tab to copy journal, missing option create reverse journal
FUN-077 | 2.2 | Financial reconciliation (reconcile entries and g/l reallocation) | Core | Standard | None | --- | --- | Done | Done | ? | No | On going | 2014-03-27 | Not possible to create Journal???. Reconcile finance entries - Not possible to use it (lack of data in the system). Functionallity seems to work.
FUN-078 | 2.3 | Financial Look-ups | Core | Standard | None | --- | --- | Done | Done | ? | No | On going | 2014-03-27 | OK
FUN-079 | 2.5 | Tax Settlement | Core | Standard | None | --- | --- | On going | On going | ? | Yes | On going | 2014-03-27 | Additional Info needed -> Not able to Approve Settlement, due to accounts that need it to be changed in Dimension?
FUN-080 | 2.6 | Posting Periode Setup | Core | Standard | None | --- | --- | On going | Open | ? | No | On going | 2014-03-27 | Finance Setup workspace does not exist ???
FUN-081 | 2.8 | Analyzer | Core | Standard | None | --- | --- | Open | Open | ? |  | Open | 2014-03-27
FUN-082 | 2.4 | Print Currency Report | Core | Standard | None | --- | --- | Done | Done | ? | No | On going | 2014-03-27 | OK
FUN-083 |  | Employes from AED to Maconomy (web services/Biz Talk) | Core | Interface | Requirements Spec, TDS |  | ? | Open | Open | ? |  | Open | 2014-03-27
FUN-084 |  | Customers to/from YellowPagiz | Core | Interface | Requirements Spec, TDS |  | ? | Open | Open | ? |  | Open | 2014-03-27
FUN-085 |  | Opportunities from CRM/Opportunity | Core | Interface | Requirements Spec, TDS |  | ? | Open | Open | ? |  | Open | 2014-03-27
FUN-086 |  | Project to/from ERM-Staffing | Core | Interface | Requirements Spec, TDS |  | ? | Open | Open | ? |  | Open | 2014-03-27
FUN-087 |  | O2C - Cash collection sent to BNP | FR, PT | Interface | ? |  | ? | Open | Open | ? |  | Open | 2014-03-27
FUN-088 |  | O2C - Cash collection sent to CGA | Local | Interface | ? |  | ? | Open | Open | ? |  | Open | 2014-03-27
FUN-089 |  | Business Process P2P - Invoices from travel suppliers | Local | Interface | ? |  | ? | Open | Open | ? |  | Open | 2014-03-27
FUN-090 |  | Accounting - ETC from DeliveriZ and Projects to DeliveriZ | Core | Interface | ? |  | ? | Open | Open | ? |  | Open | 2014-03-27
FUN-091 |  | Accounting - Balances sent to BFC | Core | Interface | TDS |  | ? | Open | Open | ? |  | Open | 2014-03-27
FUN-092 |  | Accounting - Corporate Controlling and reporting | Core | ? | ? |  | ? | Open | Open | ? |  | Open | 2014-03-27
FUN-093 |  | Integration - BI views (Oracle) | Core | Interface | TDS |  | ? | Open | Open | ? |  | Open | 2014-03-27
FUN-094 |  | Integration - Datawarehouse | Core | Interface | Requirements Spec |  | ? | Open | Open | ? |  | Open | 2014-03-27
FUN-095 |  | Integration - OBS | Core | Interface | Requirements Spec; TDS |  | ? | Open | Open | ? |  | Open | 2014-03-27
FUN-096 |  | Integration - Taiga | Core | Interface | TDS |  | ? | Open | Open | ? |  | Open | 2014-03-27
FUN-097 |  | Integration - Factoring | Core | Interface | TDS |  | ? | Open | Open | ? |  | Open | 2014-03-27
FUN-098 |  | Additional Posting Scripting - Accrued & Deferred | IT | Extension | ? |  | ? | Open | Open | ? |  | Open | 2014-03-27
FUN-099 |  | Additional Posting Scripting - VAT on ITBI | FR | Extension | ? |  | ? | Open | Open | ? |  | Open | 2014-03-27
FUN-100 |  | Additional Posting Scripting - Automatic Intercompany | Core | Extension | ? |  | ? | Open | Open | ? |  | Open | 2014-03-27
FUN-101 |  | Additional Posting Scripting - Intercompany on dimension level | Core | Extension | ? |  | ? | Open | Open | ? |  | Open | 2014-03-27
FUN-102 |  | Intercompany Work Package | Core | Extension | ? |  | ? | Open | Open | ? |  | Open | 2014-03-27
Note on I4: Elisabete Gaspar: Study based on Deltek´s documentation. Testing of Master Data (Create, Modify, Delete) and Process Data (Create New, modify, approve, block, close)
Note on J4: Elisabete Gaspar: Study based on Deltek´s documentation. Testing of Master Data (Create, Modify, Delete) and Process Data (Create New, modify, approve, block, close)
Note on K4: Elisabete Gaspar: Training by Deltek (Yes or No)

## Technical
Maconomy Support Team (Near Shore)
Transition Plan checklist
Item ID | Maconomy Module, Functionality, Processes | Scope | Solution | Documentation | Doc ID | By | Training / Support | Self-Test / Execution | Self-Test / Execution | Open Issues | Status | Estimation (Days) | Target Date | Close Date | Last update | Comments
. | Maconomy Standard Tools | . | . | . | . | . | . | Luis Dias | Luis Aguilar | . | . | . | . | . | . | .
TEC-001 | Maconomy Functional Knowlege | Core | Training | Fun. Check-List | --- | Deltek | 24-28 mar | On going | On going | Yes | On going | --- | --- | --- | 2014-03-28 | Issues with KU Training session
TEC-002 | Maconomy Functional Knowlege | PT | Training | Fun. Check-List | --- | Deltek | 24-28 mar | On going | On going | Yes | On going | --- | --- | --- | 2014-03-28 | Issues with KU Training session
TEC-003 | Workspace client installer | Core | Tool | None | ? | Deltek | No | Done | Done | No | Closed | --- | --- | --- | 2014-03-28
TEC-004 | Citrix access | Core | Tool | None | ? | Deltek | No | Done | Done | No | Closed | --- | --- | --- | 2014-03-28
TEC-005 | Java Portal | Core | Tool | None | --- | Deltek | No | Open | Open | No | Open | --- | --- | --- | 2014-03-28
TEC-006 | Maconomy environments/users | Core | Tool | None | ? | Deltek | No | Done | Done | No | Closed | --- | --- | --- | 2014-03-28
TEC-007 | Print Language - Maconomy Print Layout Tool | Core | Tool | Guide | MPL Manual | Deltek | Yes | On going | On going | No | On going | --- | --- | --- | 2014-03-28 | Documention and VarList needs to be updated regularly
TEC-008 | Business Performance Management (BPM) - Maconomy Reporting Tool | Core | Tool | None |  | Deltek | Yes | Open | Open | No | On going | --- | --- | --- | 2014-03-28
TEC-009 | InfoView | Core | Tool | Guide | WI Ref Guide | Deltek | Yes | Open | On going | No | On going | --- | --- | --- | 2014-03-28
TEC-010 | Universe Designer | Core | Tool | Guide | Universe Designer | Deltek | Yes | Open | Open | No | On going | --- | --- | --- | 2014-03-28
TEC-011 | Universe import | Core | Tool | Guide | PrintScreen Process | Deltek | Yes | Open | Open | No | On going | --- | --- | --- | 2014-03-28
TEC-012 | Universe Designer Maconomy Connection | Core | Tool | None | --- | Deltek | Yes | Open | Open | Yes | On going | --- | --- | --- | 2014-03-28 | Issues - Connection failed during training, Missing documentation
TEC-013 | Internal Maconomy DB knowledge | Core | Training | Guide (just printed) | Mconfig | Deltek | Yes | Open | On going | No | On going | --- | --- | --- | 2014-03-28 | Missing documentation (no pdf, only printed)
TEC-014 | MConfig - Maconomy Build tool | Core | Tool | Guide (just printed) | Mconfig | Deltek | Yes | On going | Done | No | On going | --- | --- | --- | 2014-03-28 | Doc: no pdf file, just printed (delivered to us in CPH)
TEC-015 | import data | Core | Tool | None | -- | Deltek | Yes | Done | Done | No | Closed |  |  |  | 2014-03-28 | Doc: no pdf file, just printed (delivered to us in CPH)
TEC-016 | dump db | Core | Tool | Guide (just printed) | Mconfig | Deltek | Yes | Done | Done | No | Closed | --- | --- | --- | 2014-03-28 | Doc: no pdf file, just printed (delivered to us in CPH)
TEC-015 | maconomy server installation | Core | Tool | None | -- |  | No | Open | Open | Yes | Open |  |  |  | 2014-03-28 | very difficult/problematic instalation
TEC-017 | Extender - Maconomy Extensions Tool | Core | Tool | None | --- | Deltek | Yes | On going | On going | Yes | On going | --- | --- | --- | 2014-03-28 | "How to" when Java / other than MDML/MWSL. Most requirements will require other tools.
TEC-018 | Languages Documentation | Core | Tool | Several Guides | Several | Deltek | Yes | Open | Done | No | On going | --- | --- | --- | 2014-03-28 | MDML, MWSL, MMSL, MCSL, MNSL (we are missing Doc. for MDSL)
TEC-019 | Extender installer and configuration | Core | Tool | Guide | Extender Handbook | Deltek | Yes | Open | On going | No | On going | --- | --- | --- | 2014-03-28 | Need laptop or VM to test (1 day)
TEC-020 | Source control knowldge | Core | Tool | Manual | gitpro | Deltek | Yes | On going | Done | No | On going | --- | --- | --- | 2014-03-28 | Documentation not Deltek specific. We can get GitPro Manual
TEC-021 | Deployment Methodologie/Process | Core | Tool | MiniGuide | Altran Consultants Guide | Deltek | Yes | Done | Done | No | Closed | --- | --- | --- | 2014-03-28
TEC-022 | Maconomy Integration | Core | Tool | None | ? | Deltek | No | Open | Open | No | On going | . | . | . | 2014-03-28 | .
TEC-023 | WebServices | Core | Tool | None | --- | Deltek | No | Open | Open | No | On going | --- | --- | --- | 2014-03-28
TEC-024 | Workflows | Core | Tool | None | --- | Deltek | No | Open | Open | No | On going | --- | --- | --- | 2014-03-28
TEC-025 | Universe Designer Maconomy Connection | Core | Tool | None | --- | Deltek | Yes | Open | Open | Yes | Open | --- | --- | --- | 2014-03-28 | Issues - Connection failed during training; our BO instalation can't connect to Maconomy Database
TEC-026 | Data Warehouse Integration | Core | Tool | ? |  | Deltek | No | Open | Open | No | On going | --- | --- | --- | 2014-03-28
. | Maconomy Usage of Tools - Tasks | . | . | . | . | . | . | . | . | . | On going | . | . | . | . | .
TASK-001 | Job Invoice/Draft Invoice Layout | IT | Layout | Bugzilla / invoice mock | 1174 | Altran | Yes | --- | Done | No | Closed | --- | 2014-02-15 | 2014-02-15 | 2014-03-28 | Done, in PREPROD. Updates/Req. Changes/Bug fixes being managed by Deltek
TASK-002 | Report Credit Notes Reasons | Core | Report | None | 1069 | Altran | Yes | --- | Done | No | Closed | --- | --- | --- | 2014-03-28 | Done
TASK-003 | Disable Print Draft button | PT | Extensions | Bugzilla | 1815 | Altran | Yes | --- | Done | No | Closed | --- | 2014-03-15 |  | 2014-03-28 | Done
TASK-004 | Purchase Process Creation | PT | Extensions | Bugzilla | 1614 | Altran | Yes | --- | Done | No | Closed | --- | 2014-03-15 | 2014-03-15 | 2014-03-28 | Done
TASK-005 | Text 5 option list in Project Creation Wizard | PT | Extensions | Spec | G007/1816 | Altran | Yes | --- | Done | No | Closed | --- | 2014-03-15 | 2014-03-15 | 2014-03-28 | Done
TASK-006 | Nearshore Local spec3 mandatory | PT | Extensions | Spec | G003/1822 | Altran | Yes | --- | Done | No | Closed | --- | 2014-03-15 | 2014-03-15 | 2014-03-28 | Done
TASK-007 | InternalCredits | PT | Extensions | Spec | G005/1699 | Altran | No | --- | Done | No | Closed | --- | 2014-03-15 | 2014-03-15 | 2014-03-28 | Finished by Deltek (adv. Extension)
TASK-008 | Gross Margin Summary Report | PT | Layout | ? | NO Doc. | Altran | Yes | --- | On going | Yes | On going | --- | 2014-03-15 |  | 2014-03-28 | Waiting for KU clarification
TASK-009 | Print Invoice Layout | PT | Layout | None | --- | Altran | Yes | Done | --- | No | On going | --- | 2014-03-15 |  | 2014-03-28 | Done, awaits tests
TASK-010 | Print Credit Memo | PT | Layout | None | --- | Altran | Yes | Done | --- | No | On going | --- | 2014-03-15 |  | 2014-03-28 | Done, awaits tests
TASK-011 | Print Payment Order | PT | Layout | None | --- | Altran | Yes | On going | --- | No | On going | --- | 2014-03-15 |  | 2014-03-28
TASK-012 | Print Layout - General Expenses | PT | Layout | None | --- | Altran | Yes | On going | --- | No | On going | --- | 2014-03-15 |  | 2014-03-28
TASK-013 | FixedAssets | PT | Extensions | Spec | G004 | Altran | Yes | Not done | --- | Yes | On going | --- | --- | --- | 2014-03-28 | To be done by Deltek due to Java issue
TASK-014 | General Expenses (3 prints) | PT | Layout | ? | ? | Altran | Yes | On going | --- | No | On going | --- | 2014-03-28 |  | 2014-03-28 | OK
TASK-015 | Invoice specification | PT | Layout | ? | ? | Altran | Yes | On going | --- | No | On going | --- | 2014-03-28 |  | 2014-03-28 | Novo layout. AguardaDeltek.
TASK-016 | Zero Invoices (edit) | PT | Layout | ? | ? | Altran | Yes | On going | --- | No | On going | --- | 2014-03-28 |  | 2014-03-28 | Novo layout. AguardaDeltek.
TASK-017 | Approve Reminders | PT | Layout | ? | ? | Altran | Yes | On going |  | No | On going | --- | 2014-03-28 |  | 2014-03-28
TASK-018 | Statutory - Account Type Code | PT | Extensions | Bugzilla | 2008 | Altran | No | --- | Done | No | On going | --- | 2014-03-28 |  | 2014-03-28 | Ok: (to be) finished by Deltek (adv. Extension)
TASK-019 | SubCustomer Creation Wizard Update | PT | Extensions | asked by Jenny | NO Doc. | Altran | Yes | Done | Done | No | Closed | --- | 2014-03-28 | 2014-03-24 | 2014-03-28 | OK
TASK-020 | Rename 2 fields in the Company Card | Core | Extensions | Bugzilla | 2072 | Altran | Yes | Done | Done | No | Closed | --- | 2014-03-28 | 2014-03-24 | 2014-03-28 | OK
TASK-021 | Changes to Project Information | PT | Extensions | Bugzilla | 2006 | Altran | Yes | Done | Done | No | Closed | --- | 2014-03-28 | 2014-03-21 | 2014-03-28 | OK
TASK-022 | More Changes to Project Information | PT | Extensions | asked by Jenny | NO Doc. | Altran | Yes | Done | Done | No | Closed | --- | 2014-03-28 | 2014-03-24 | 2014-03-28 | OK
TASK-023 | Reminder layouts | PT | Layout |  |  | Altran | Yes | Done | Done | No | On going | --- | --- | --- | 2014-03-28 | OK
Note on H4: Elisabete Gaspar: Training or on-site support by Deltek (Yes or No)
Note on I4: Elisabete Gaspar: Self-training, self-study and execution
Note on J4: Elisabete Gaspar: Self-training, self-study and execution

## List of Customizations
Maconomy Support Team (Near Shore)
Transition Plan checklist
Item ID | Maconomy Module, Functionality, Processes | Scope | Solution | Documentation | Doc ID | Done by Deltek | Functional Knowledge | Technical Knowledge | Training | Status | Notes | Comments
. | . | . | . | . | . | Yes | Done |  | No |  |  | Issues, missing points, any relevant info
| Document Layouts - Invoice / Credit Memo | Local | Layouts | ? |  | ? | None | None | None | Open
| Document Layouts - ? | Local | Layouts | ? |  | ? | None | None | None | Open
| Finance - Balance Sheet | Core | Reports |  | 1 - 1a | ? | None | None | None | Open
| Finance - Local Balance Sheet | Local | Reports |  | 1 - 1b | ? | None | None | None | Open
| Finance - Profit & Loss | Core | Reports |  | 2 - 2a | ? | None | None | None | Open
| Finance - Profit & Loss, Periodic | Core | Reports |  | 2 - 2b | ? | None | None | None | Open
| Finance - Profit & Loss, Fiscal year | Core | Reports |  | 2 - 2c | ? | None | None | None | Open
| Finance - Profit & Loss, By Dimension | Core | Reports |  | 2 - 2d | ? | None | None | None | Open
| Finance - Local Profit & Loss | Core | Reports |  | 2 - 2e | ? | None | None | None | Open
| Finance - Local Profit & Loss, Periodic | Core | Reports |  | 2 - 2f | ? | None | None | None | Open
| Finance - Local Profit & Loss, Fiscal year | Core | Reports |  | 2 - 2g | ? | None | None | None | Open
| Finance - Local Profit & Loss, By Dimension | Core | Reports |  | 2 - 2h | ? | None | None | None | Open
| Finance - Trial Balance | Core | Reports |  | 3 - 3a | ? | None | None | None | Open
| Finance - Trial Balance Analysis | Core | Reports |  | 3 - 3b | ? | None | None | None | Open
| Finance - Trial Balance No Grouping | Core | Reports |  | 3 - 3c | ? | None | None | None | Open
| Finance - Finance transactions | Core | Reports |  | 4 - 4a | ? | None | None | None | Open
| Project Cost - WIP Aging | Core | Reports |  | 5 - 5a | ? | None | None | None | Open
| Project Cost - WIP Aging, by Dimension | Core | Reports |  | 5 - 5b | ? | None | None | None | Open
| Project Cost - WIP Periodic | Core | Reports |  | 5 - 5c | ? | None | None | None | Open
| Project Cost - WIP Transactions | Core | Reports |  | 6 - 6a | ? | None | None | None | Open
| Project Cost - Project Profitability Summary | Core | Reports |  | 7 - 7a | ? | None | None | None | Open
| Project Cost - Project Profitability Transactions | Core | Reports |  | 7 - 7b | ? | None | None | None | Open
| Project Cost - Customer Profitability | Core | Reports |  | 8 - 8a | ? | None | None | None | Open
| Project Cost - Customer Profitability, by Customer | Core | Reports |  | 8 - 8b | ? | None | None | None | Open
| Project Cost - Customer Profitability Comparison, by Customer | Core | Reports |  | 8 - 8c | ? | None | None | None | Open
| Project Cost - Revenue Analysis | Core | Reports |  | 9 - 9a | ? | None | None | None | Open
| Project Cost - Bill to Customer Distribution | Core | Reports |  | 10 - 10a | ? | None | None | None | Open
| Project Cost - Contact Company List | Core | Reports |  | 11 - 11a | ? | None | None | None | Open
| Project Cost - Project List | Core | Reports |  | 12 - 12a | ? | None | None | None | Open
| Project Cost - Daily Flash | Core | Reports |  | 13 - 13a | ? | None | None | None | Open
| Project Cost - Main Job, Sub Job Overview | Core | Reports |  | 14 - 14a | ? | None | None | None | Open
| Project Cost - Project Employee | Core | Reports |  | 15 - 15a | ? | None | None | None | Open
| Project Cost - Invoiced Registrations | Core | Reports |  | 16 - 16a | ? | None | None | None | Open
| Customer - AR Ageing | Core | Reports |  | 17 - 17a | ? | None | None | None | Open
| Customer - AR Ageing by Dimension | Core | Reports |  | 17 - 17b | ? | None | None | None | Open
| Customer - AR Aging Details by Dimension | Core | Reports |  | 17 - 17c | ? | None | None | None | Open
| Customer - AR Aging Summary by Dimension | Core | Reports |  | 17 - 17d | ? | None | None | None | Open
| Customer - AR Periodic | Core | Reports |  | 17 - 17e | ? | None | None | None | Open
| Customer - AR Transactions | Core | Reports |  | 17 - 17f | ? | None | None | None | Open
| Customer - Customer Invoice Status | Core | Reports |  | 18 - 18a | ? | None | None | None | Open
| Customer - Customer Invoices | Core | Reports |  | 18 - 18b | ? | None | None | None | Open
| Customer - Customer Statement | Core | Reports |  | 18 - 18c | ? | None | None | None | Open
| Customer - Cash Receipts | Core | Reports |  | 19 - 19a | ? | None | None | None | Open
| Customer - Bank Reconciliation | Core | Reports |  | 20 - 20a | ? | None | None | None | Open
| Vendor - AP Aging | Core | Reports |  | 21 - 21a | ? | None | None | None | Open
| Vendor - AP transactions | Core | Reports |  | 21 - 21b | ? | None | None | None | Open
| Employee - Unsubmitted Time | Core | Reports |  | 22 - 22a | ? | None | None | None | Open
| Employee - Timesheet overview | Core | Reports |  | 23 - 23a | ? | None | None | None | Open
| Employee - Timesheet Status (by week) | Core | Reports |  | 24 - 24a | ? | None | None | None | Open
| Subscription - Subscription | Core | Reports |  | 25 - 25a | ? | None | None | None | Open
| VATNumber | PT | Extension | Specification | PT G001 | ? | None | None | None | Open
| Vendor PaymentReceipt | PT | Extension | Specification | PT G002 | ? | None | None | None | Open
| Nearshore | PT | Extension | Specification | PT G003 | ? | None | None | None | Open
| FixedAssets | PT | Extension | Specification | PT G004 | ? | None | None | None | Open
| InternalCredits | PT | Extension | Specification | PT G005 | ? | None | None | None | Open
| VATTexts | PT | Extension | Specification | PT G006 | ? | None | None | None | Open
| LOB_CM | PT | Extension | Specification | PT G007 | ? | None | None | None | Open
| FactoringIBANexts | PT | Extension | Specification | PT G008 | ? | None | None | None | Open
| CustomerReceipts | PT | Extension | Specification | PT G009 | ? | None | None | None | Open
| BlockingInvoices | PT | Extension | Specification | PT G010 | ? | None | None | None | Open
| 13MonthPeriod | PT | Extension | Specification | PT G011 | ? | None | None | None | Open
| StatisicalCode | PT | Extension | Specification | PT G012 | ? | None | None | None | Open
| CreditNoteReason | PT | Extension | Specification | PT G013 | ? | None | None | None | Open
| Mileage_portal | PT | Extension | Specification | PT G015 | ? | None | None | None | Open
| Allowance | PT | Extension | Specification | PT G016 | ? | None | None | None | Open
| General expenses_portal | PT | Extension | Specification | PT G017 | ? | None | None | None | Open
| Timesheet | PT | Extension | Specification | PT G018 | ? | None | None | None | Open
| Absence management_portal | PT | Extension | Specification | PT G021 | ? | None | None | None | Open
| PortalToDos | PT | Extension | Specification | PT G022 | ? | None | None | None | Open
| Holiday Accrual | PT | Extension | Specification | PT G023 | ? | None | None | None | Open
| Generallocal_Specification | PT | Extension | Specification | PT | ? | None | None | None | Open
| Report para projetos ADM 3&4 + NSH | PT | Reports | GAP | RPT01 | ? | None | None | None | Open
| WIP Aging | PT | Reports | GAP | RPT05 | ? | None | None | None | Open
| End customer in reports | PT | Reports | GAP | RPT06 | ? | None | None | None | Open
| TOP10 | PT | Reports | GAP | RPT07 | ? | None | None | None | Open
| Turnover/Margem/Daily Sales por Industria (Cliente Externo e Interno) | PT | Reports | GAP |  | ? | None | None | None | Open
| Gross Margin Summary por Departamento | PT | Reports | GAP |  | ? | None | None | None | Open
| Rate por Cliente | PT | Reports | GAP |  | ? | None | None | None | Open
| Factoring Export File | PT | Interface | Specification | PT INT02 | ? | None | None | None | Open
| Payroll Interface | PT | Interface | Specification | PT INT01 | ? | None | None | None | Open
| Absent / Holidays & Expenses | PT | Interface | Specification |  | ? | None | None | None | Open
| Employee Cost | PT | Interface | ? |  | ? | None | None | None | Open
| SEPA - Banking | PT | Interface | ? |  | ? | None | None | None | Open
| Fiscale - Liquidazione IVA (Mensile) | IT | Report |  |  | ? | None | None | None | Open | Report Navision
| Fiscale - Registro IVA Acquisti UE (Mensile) | IT | Report |  |  | ? | None | None | None | Open | Report Navision
| Fiscale - Registro IVA Acquisti EXTRA UE (Mensile) | IT | Report |  |  | ? | None | None | None | Open | Report Navision
| Fiscale - Registro IVA Acquisti Italia (Mensile) | IT | Report |  |  | ? | None | None | None | Open | Report Navision
| Fiscale - Registro IVA Vendite su Acq. UE (Mensile) | IT | Report |  |  | ? | None | None | None | Open | Report Navision
| Fiscale - Registro IVA Vendite Extra UE (Mensile) | IT | Report |  |  | ? | None | None | None | Open | Report Navision
| Fiscale - Registro IVA Vendite Italia (Mensile) | IT | Report |  |  | ? | None | None | None | Open | Report Navision
| Fiscale - Comunicazione IVA (Mensile) | IT | Report |  |  | ? | None | None | None | Open | Manuale
| Fiscale - Libro Giornale (Mensile) | IT | Report |  |  | ? | None | None | None | Open | Report Navision
| Fiscale - Ritenuta d'acconto (Mensile) | IT | Report |  |  | ? | None | None | None | Open | Report Navision
| Fiscale - Certificazione versamento RA (Annuale) | IT | Report |  |  | ? | None | None | None | Open | Report Navision
| Fiscale - Registro cespiti (Mensile) | IT | Report |  |  | ? | None | None | None | Open | Manuale
| Fiscale - Intrastat (Mensile) | IT | Report |  |  | ? | None | None | None | Open | Manuale
| Fiscale - Blacklist (Mensile) | IT | Report |  |  | ? | None | None | None | Open | Manuale
| Civilistico - Riclassifica bilancio in 4^ direttiva (Mensile / Annuale) | IT | Report |  |  | ? | None | None | None | Open | Manuale
| Custom - DSO | Core | Report |  | #1 | ? | None | None | None | Open | Requested by France, Tool BPM
| Custom - Group Cockpit | Core | Report |  | #2 | ? | None | None | None | Open | Requested by France, Tool BPM
| Custom - Detailed P&L | Core | Report |  | #3 | ? | None | None | None | Open | Requested by France, Tool GL Report
| Custom - Periodic P&L in BFC format | Core | Report |  | #4 | ? | None | None | None | Open | Requested by , Tool BPM
| Custom - FTE and Rates | Core | Report |  | #5 | ? | None | None | None | Open | Requested by France, Business Case, Tool BPM
| Custom - Operating Cockpit | Core | Report |  | #5.1; R7 | ? | None | None | None | Open | Requested by France, Tool BPM
| Custom - Focus Invoicing and unbilled | Core | Report | Report Design | #5.2; R8 | ? | None | None | None | Open | Requested by France, Tool BPM
| Custom - Invoicing rate razionalization | Core | Report |  | #5.3; R9 | ? | None | None | None | Open | Requested by France, Tool BPM
| Custom - Utilization and FTE | Core | Report |  | #6 | ? | None | None | None | Open | Requested by France, Tool BPM
| Custom - Headcounts and FTE | Core | Report |  | #7 | ? | None | None | None | Open | Requested by France, Tool BPM
| Custom - Headcount by Company | Core | Report |  | #8 | ? | None | None | None | Open | Requested by France, Tool BPM
| Custom - Hires & Departures | Core | Report |  | #9 | ? | None | None | None | Open | Requested by France, Tool BPM
| Custom - CM | Core | Report |  | #10 | ? | None | None | None | Open | Requested by Business Case, Tool BPM
| Custom - Globally Unique Program ID | Core | Report |  | #11 | ? | None | None | None | Open | Requested by Business Case, Tool BPM
| Custom - Project Direct Margin | Core | Report |  | #12 | ? | None | None | None | Open | Requested by Spain, Tool BPM
| Custom - Aged WIP report with comments | Core | Report |  | #13 | ? | None | None | None | Open | Tool Existing BPM
| Custom - Customer PO Reporting | Core | Report |  | #14 | ? | None | None | None | Open | Tool BPM/To do
| Custom - Backlog | Core | Report |  | #15 | ? | None | None | None | Open | Requested by Business Case, Tool BPM
| Custom - GL Ageing report | Core | Report |  | #16 | ? | None | None | None | Open | Tool BPM
| Interface - OBS (from); Dimension Groupings / Organization | Core | Extension |  |  | ? | None | None | None | Open | Webservice, Real Time
| Interface - AED (from); Employees & Subcontractors | Core | Extension | Specification |  | ? | None | None | None | Open | Webservice, Real Time
| Interface - YellowPagiZ (from); Customers | Core | Extension |  |  | ? | None | None | None | Open | Webservice, Real Time
| Interface - CRM (from); Opportunities | Core | Extension | Specification |  | ? | None | None | None | Open | Webservice, Real Time
| Interface - ERM (from); Staff Allocations | Core | Extension |  |  | ? | None | None | None | Open | Webservice, Real Time
| Interface - From Ulysses To ERM; Staff Allocations | Core | Extension |  |  | ? | None | None | None | Open | Webservice, Real Time
| Interface - DeliveriZ (from); TimeSheets & ETC | Core | Extension |  |  | ? | None | None | None | Open | File, Real Time
| Interface - AMEX (from); Vendor Invoices | Core | Extension |  |  | ? | None | None | None | Open | File, Weekly or Monthly
| Interface - Factoring (from); Customer Invoices/Balances | Core | Extension |  |  | ? | None | None | None | Open | File, Weekly or Monthly
| Interface - BFC (from); Financial Data | Core | Extension |  |  | ? | None | None | None | Open | File, Weekly or Monthly
| Interface - BI (from); Management Reporting | Core | Extension |  |  | ? | None | None | None | Open | TBD, Weekly or Monthly
| Interface - Cash management (TAIGA) (To); Cash movement | Core | Extension |  |  | ? | None | None | None | Open | File, Real Time
| Interface - Local HR systems (from); TimesSheet | Core | Extension |  |  | ? | None | None | None | Open | File, Real Time
| Interface - Country Specific Portals (from); Timesheet/Expensesheet/Requisition | Core | Extension |  |  | ? | None | None | None | Open | File, Real Time
| Interface - Local Payroll (from); Payroll | Core | Extension |  |  | ? | None | None | None | Open | File, Monthly
| Interface - DWH (Data Warehouse) | Core | Extension |  |  | ? | None | None | None | Open
| Interface - Payroll (from); ANADIP | IT | Extension |  |  | ? | None | None | None | Open | txt, Monthly
| Interface - Payroll (from); PRIS | IT | Extension |  |  | ? | None | None | None | Open | txt, Monthly
| Interface - Payroll (from); PRIT | IT | Extension |  |  | ? | None | None | None | Open | txt, Monthly
| Interface - WEB Portal (from); Timesheets (1) | IT | Extension |  |  | ? | None | None | None | Open | DB, Monthly
| Interface - WEB Portal (from); Timesheets (2) | IT | Extension |  |  | ? | None | None | None | Open | DB, Monthly
| Interface - Biz To WEB Portal; Projects | IT | Extension |  |  | ? | None | None | None | Open | xml, On-Demand
| Interface - WEB Portal (from); Job Management (1) | IT | Extension |  |  | ? | None | None | None | Open | DB, On-Demand
| Interface - WEB Portal (from); Job Management (2) | IT | Extension |  |  | ? | None | None | None | Open | DB, On-Demand
| Interface - From WEB Portal (from); Job Management (3) | IT | Extension |  |  | ? | None | None | None | Open | DB, On-Demand
| Interface - external (from); Purchasing Invoice | IT | Extension |  |  | ? | None | None | None | Open | csv, Monthly
| Interface - WEB Portal (from); Employment requests | IT | Extension |  |  | ? | None | None | None | Open | DB, On-Demand
| Interface - WEB Portal (from); Salary Increase requests | IT | Extension |  |  | ? | None | None | None | Open | DB, On-Demand
| Interface - WEB Portal (from); Pre-Invoice approval | IT | Extension |  |  | ? | None | None | None | Open | DB, On-Demand
| Interface - external To WEB Portal; Document management | IT | Extension |  |  | ? | None | None | None | Open | DB, On-Demand
| Interface - Payroll (from); Awards | IT | Extension |  |  | ? | None | None | None | Open | xlsx, Monthly
| Interface - To Payroll; Hours (1) | IT | Extension |  |  | ? | None | None | None | Open | txt, Monthly
| Interface - To Payroll; Hours (2) | IT | Extension |  |  | ? | None | None | None | Open | txt, Monthly
| Interface - To Payroll; Reimboursement | IT | Extension |  |  | ? | None | None | None | Open | txt, Monthly
| Interface - To External; Ticket restaurant | IT | Extension |  |  | ? | None | None | None | Open | txt, Monthly
| Interface - To Factor; Factor (1) | IT | Extension |  |  | ? | None | None | None | Open | csv, 2-3 times a month
| Interface - To Factor; Factor (2) | IT | Extension |  |  | ? | None | None | None | Open | csv, 2-3 times a month
| Interface - To Group; DUNS Clients | IT | Extension |  |  | ? | None | None | None | Open | xlsx, Monthly
| Interface - To Group; Hesperides | IT | Extension |  |  | ? | None | None | None | Open | xlsx, Monthly
| Interface - To Users; Employment termination | IT | Extension |  |  | ? | None | None | None | Open | xlsx, Daily
| Interface - To KM; Knowledge Managemet (1) | IT | Extension |  |  | ? | None | None | None | Open | DB, Daily
| Interface - To KM; Knowledge Managemet (2) | IT | Extension |  |  | ? | None | None | None | Open | DB, Daily
| Interface - To KM; Knowledge Managemet (3) | IT | Extension |  |  | ? | None | None | None | Open | DB, Daily
| Interface - To External; Bank Payment | IT | Extension |  |  | ? | None | None | None | Open | txt, On-Demand
| Interface - WebPortal To External; HR Employee Documents | IT | Extension |  |  | ? | None | None | None | Open | xlsx+attach, 2-3 times a month
| Custom - G&A | Core | Report | Report Design | r5 | ? | None | None | None | Open
| Custom - Focus Invoicing and unbilled | Core | Report | Report Design | r24 | ? | None | None | None | Open
| Custom - Standard FTE |  |  |  | R5 | ? | None | None | None | Open
| Custom - Dashboard Sales | Core | Report |  | #5.3; R25 | ? | None | None | None | Open
| Custom - ITBI per OBS | Core | Report |  | #5.3; R61 | ? | None | None | None | Open
| Custom - Dashboard Sales BFC Bridge | Core | Report |  | #5.3; 62 | ? | None | None | None | Open
| Custom - AR reconciliation | Core | Report |  | #5.3; R63 | ? | None | None | None | Open